## TestCases
Name of the Project | Speed Car Racing |  | Test Cases
Created By | Mahaboob Basha
Created Date | 2024-03-03
Reviewed By
Test Case_ID | Test Case Description | Test Steps | Expected Result | Actual Result | Status | Executed By | Executed Date | Comments(if any)
TC_01 | Verify that game is downloaded. | 1.Open the Playstore. 2.Install the game | Game should be installed without any errors. | Game is installing without any issues. | Pass | Mahaboob Basha | 2024-09-03
TC_02 | Verify that after launching the game Company logo is displaying. | 1.Open the game. 2.Check Brand logo on screen. | Game should be display company logo. | Game not displaying logo of the company | Fail | Mahaboob Basha | 2024-09-03
TC_03 | Verify that game is launching without any crash or error. | 1.Install the game (APK). | Game should be launched without any bugs. | Game is launched without any bugs. | Pass | Mahaboob Basha | 2024-09-03
TC_04 | Verify that in menu page all the buttons are working fine. | 1.Open the Game. 2.Check menu page. | Menu page buttons such as Play or Start,settings,Coins should be work without any errors. | All the buttons are working fine. | Pass | Mahaboob Basha | 2024-09-03
TC_05 | Verify that create identity is working. | 1.Open the Game. 2.Choose name and Confirm. | Identity should be created and displayed menu page. | Create identity is working. | Pass | Mahaboob Basha | 2024-09-03
TC_06 | Verify that settings page all the functionalities are added as per CRS. | 1.Open the Game. 2.Click on settings. | Settings page should be added with all the fucntionalities.(Sound,Sensitivity,Graphics,Privacy Policy,Game controls) | All functionalities are added as per CRS. | Pass | Mahaboob Basha | 2024-09-03
TC_07 | Verify that sound can be selected in different audio tracks. | 1.Open the Game. 2.Click on settings. 3.Click on Sound. | Sounds should be changed according to user. | Sounds are changing according to the user. | Pass | Mahaboob Basha | 2024-09-03
TC_08 | Verify that Sensitivity can be increased and decreased. | 1.Open the Game. 2.Click on settings. 3.Click on Sensitivity. | Sensitivity should be changed as user control. | Sensitivity is not changing as per user. | Fail | Mahaboob Basha | 2024-09-03
TC_09 | Verify that Privacy policy is working. | 1.Open the Game. 2.Click on settings. 3.Click on Privacy Policy. | Privacy policy should display all the guidelines of company. | Privacy policy is working and displaying the guidlines of the company. | Pass | Mahaboob Basha | 2024-09-03
TC_10 | Verify that Graphics can be changed or not. | 1.Open the Game. 2.Click on settings. 3.Click on graphics. | Graphics should work as per user user changes. | Graphics are not changing when we select different modes of graphics. | Fail | Mahaboob Basha | 2024-09-03
TC_11 | Verify that Game controls can be managed. | 1.Open the Game. 2.Click on settings. 3.Click on Game Controls. | Game controls should be controlled by User. | Game controls are not able manage. | Fail | Mahaboob Basha | 2024-09-03
TC_12 | Verify that store page all IAP buttons are working. | 1.Open the Game. 2.Click on coins button. 3.Click on IAP. | All the IAP should revert to payment popup. |  | Progress | Mahaboob Basha | 13-03-2024 | Still not added the AD set up in the game.
TC_13 | Verify that Start button is working. | 1.Open the Game. 2.Click on coins button. | Start button should display Car upgrade page. | Start button is working as expected. | Pass | Mahaboob Basha | 13-03-2024
TC_14 | Verify that upgrade button is working | 1.Open the game. 2.Click on Start and then Upgrade. | Upgrade button should display all functionalities present. | Upgrade page is working as expected. | Pass | Mahaboob Basha | 13-03-2024
TC_15 | Verify that upgrade functionalities(Nitro,Chasis,Engine,Gearbox) are working. | 1.Open the game. 2.Click on Start and then Upgrade. | Upgrade functionalities should improve performance of car. | Upgrade page functionalities are working as expected. | Pass | Mahaboob Basha | 13-03-2024
TC_16 | Verify that Cars can be customized or not. | 1.Open the game. 2.Click on Start . 3.Click on cars. | Car should be changed according user customization. | Cars are getting customized as per user. | Pass | Mahaboob Basha | 13-03-2024
TC_17 | Verify that colors of the car can be changed. | 1.Open the game. 2.Click on Start . 3.Click on Colors. | Car color should be customized as per user. | Car colors are getting customized as per user. | Pass | Mahaboob Basha | 13-03-2024
TC_18 | Verify that stickers can be customized. | 1.Open the game. 2.Click on Start . 3.Click on Stickers. | Car stickers should be added to the car as per user. | Car stickers are getting customized as per user. | Pass | Mahaboob Basha | 13-03-2024
TC_19 | Verify that tyre disc can be customized. | 1.Open the game. 2.Click on Start . 3.Click on tyres. | Car tyre disc should be change as user changes. | Car tyre disc are getting customized as per user. | Pass | Mahaboob Basha | 13-03-2024
TC_20 | Verify that car is rotating or not in menu and upgrade pages. | 1.Open the game. 2.Click on Start. 3.Rotate the car. | Car position should be changed according to user direction in 360°. | Car is navigating as user direction. | Pass | Mahaboob Basha | 13-03-2024
TC_21 | Verify that Career and Challenges modes are working. | 1.Open the game. 2.Click on Start. 3.Click on Play. | Two modes of gameplay should be displayed different challenges. | Career and challenges modes are working . | Fail | Mahaboob Basha | 14-03-2024 | In challenge mode level's are not arranged.
TC_22 | Verify that Career mode contains game level's. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Career mode | Career mode should display all game level's. | Career mode is displaying all the level's. | Pass | Mahaboob Basha | 14-03-2024
TC_23 | Verify that each level should contain Objective. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Career mode | Clicking each level should display different objectives to the user. | There is no objective for any level in the game. | Fail | Mahaboob Basha | 14-03-2024
TC_24 | Verify that game controls are working in INGAME. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Career mode 5.Click on Race. | In game controls should be working while playing the game. | Controls are working fine in game. | Pass | Mahaboob Basha | 14-03-2024
TC_25 | Verify that pause button is working . | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Career mode 5.Click on Race. | Pause page should work with all functionalities included in page.(Restart,Resume,Menu,Controls) | All the functionalities in pause page are working as expected. | Pass | Mahaboob Basha | 14-03-2024
TC_26 | Verify that game sound and music are played correctly. | 1.Open the game. 2.Click on Start. 3.Click on Play. | Sound should be matched with game graphics and movement of the car. | Music and sound are merging in game. | Fail | Mahaboob Basha | 14-03-2024
TC_27 | Verify that speedometer is changing for car. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Race. | Speedometer should be change according user speed control. | Speedometer is changing in game according to speed control. | Pass | Mahaboob Basha | 14-03-2024
TC_28 | Verify that position of the car in race is displaying. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Race. | Car position should display to the user in racing. | Car position is displaying in game. | Pass | Mahaboob Basha | 14-03-2024
TC_29 | Verify that Drifting car is noticeable. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Race. 5.Drift the car. | Drift car should be displayed in number with distance covered. |  | Progress | Mahaboob Basha | 14-03-2024 | Drift count need to be check in game.
TC_30 | Verify that Game Duration and Percentage to finish is displaying. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Race. | Game play should show time taken and percentage to reach end game. | In game duration and percentage finish is displaying as expected. | Pass | Mahaboob Basha | 14-03-2024
TC_31 | Verify that Pink line bar on road is working. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Race. | Car should move faster than normal with high speed. | Car is moving faster but is displaying lesser than usual speed. | Fail | Mahaboob Basha | 14-03-2024
TC_32 | Verify that Blue nitro is working correctly. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Race. | Car should increase speed and move faster when user uses nitro. | Car speed is increasing while performing nitro functionality. | Pass | Mahaboob Basha | 14-03-2024
TC_33 | Verify that Level complete page displays all achievements. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Finish the Race. | Level complete should display all Drift,Speed,win,bravery and Total points to the user. | Level complete is displaying all the achievements. | Pass | Mahaboob Basha | 14-03-2024
TC_34 | Verify that after results page Player profile increasing it's bar according to the points achieved in game. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Finish the Race. 5.Check profile level. | Player profile level should be increased after every level depends performance from level. | Player profile is increasing but points are adding random. | Fail | Mahaboob Basha | 14-03-2024 | win 1000 speed 100 This info is previous level below is current level Speed 250 win 26200 | D 100 B 50 S 300 W 26690
TC_35 | Verify that achieved points are added total points in the game. | 1.Open the game. 2.Check the total points. | Total Reward points should increase after every race. | achieved points are adding to the total points. | Pass | Mahaboob Basha | 14-03-2024
TC_36 | Verify that Race results displaying after Level Complete. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Finish the Race. | Race results should show player name,duration of the game,position of the player and Car model. | Results are displaying as expected. | Pass | Mahaboob Basha | 14-03-2024
TC_37 | Verify that Challenge mode is displaying different challenges. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Challenge mode | Challenge mode should display challenges with entry fee to play the game. |  | Progress | Mahaboob Basha | 14-03-2024 | Need to work on this in next update.
TC_38 | Verify that each challenge level have events to finish the game. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Click on Challenge level. | Challenge level should display requirement to play and task to finish the race among the racers. |  | Progress | Mahaboob Basha | 14-03-2024 | Need to work on this in next update.
TC_39 | Verify that after level finish next level popup is displaying. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Finish the race | Next level unlocked popup should be displayed. | Next level unlocked popup is opening only for few levels. | Fail | Mahaboob Basha | 14-03-2024
TC_40 | Verify that each car is increasing it's speed in game. | 1.Open the game. 2.Click on Start. 3.Click on Play. 4.Check speed of car. | Car speed should be increased and vary from each car. | Car speed is increasing for each level. | Pass | Mahaboob Basha | 14-03-2024

## Bugs
Bug Report
Project Name | Car Racing Ultimate
Detected by | Mahaboob Basha
Assigned to
Play Store Link | Not uploaded Yet
Defect_ID | Summary | Detected Date | Severity | Priority | Tester Status | Dev Status | Build Version | Defect type | Expected Result | Actual Result | Comments if any
Defect_01 | In Level selection page we are unable replay the completed level's. | 2024-09-03 | Critical | Medium | Closed | Closed | 0.1 | Functional | We should be able to play completed level's. | We are not able to play the game again after level completion.
Defect_02 | Sound on/off functionality is working only in switched off condition. | 2024-09-03 | Minor | Low | Closed | Closed | 0.1 | Functional | Sound functionality should work in both conditons (ON/OFF) | Sound functionality is working only to off the sound.
Defect_03 | Settings and store buttons sizes are very small and hard to perform functionality. | 2024-09-03 | Minor | Low | Closed | Closed | 0.1 | Functional | Icons should be perfect size for better visiblity to the user. | Icons are very small and unable to perform functionality.
Defect_04 | In upgrade page,icon button for upgrade are unable click exactly. | 2024-09-03 | Minor | Low | Closed | Closed | 0.1 | Functional | Button should be in size to perform functionality. | Buttons are too tiny to perform functionality.
Defect_05 | Unknown Player profile is displaying in upgrade page | 2024-09-03 | Minor | Low | Closed | Closed | 0.1 | Non-Functional | Profile page should be similar to the user information. | Unknown profile info is displaying in upgrade page.
Defect_06 | In pause page sound controls are applying to all over the game.(Menu page,upgrade, | 2024-09-03 | Critical | High | Closed | Closed | 0.1 | Functional | Sound controls should be able apply for the ingame functionality. | Sound controls are applying to the entire game.
Defect_07 | While passing pink bars in game on road white particles effect is animated over the car. | 2024-09-03 | Critical | High | Closed | Closed | 0.1 | Functional | While crossing the highlighted bars in game particle effect should be feel good. | Particles effect is not as expected and not good in end user point of view.
Defect_08 | Each car power is increasing more than it's range. | 2024-09-03 | Critical | Medium | Closed | Closed | 0.1 | Functional | Car power should be fixed individually for each car. | Car power is more than its fixed range in game.
Defect_09 | In menu page sensitivity for car rotation is high. | 2024-09-03 | Minor | Low | Closed | Closed | 0.1 | Functional | Sensitivity is should be normal for better experience of game. | Sensitivity is more, hard to perform and feel the gaming experience.
Defect_10 | Car right side tail lamp missing for lamborgini.(5th) | 2024-11-03 | Minor | Low | Closed | Closed | 0.1 | Functional | Lights should be for every car in game. | Lights are missing for a 5th car in game.
Defect_11 | In upgrade page car lights material is missing for 4th car. | 2024-11-03 | Minor | Low | Closed | Closed | 0.1 | Functional | Materials for car images should be arranged. | Materials for car images are missing.
Defect_12 | Car tyres are merging in road. | 2024-11-03 | Minor | Low | Closed | Closed | 0.1 | Non-Functional | Car tyres should be on road for better experience. | Car tyres are merging in road
Defect_13 | Car-20th tail lamps are not lightning both sides. | 2024-11-03 | Major | Low | Closed | Closed | 0.1 | Functional | Car lights be lightning in game. | Car lights are not lightning.
Defect_14 | Back button size is small in store page. | 13-03-2024 | Minor | Low | Closed | Closed | 0.1 | Functional | Back button size should be exact size in' store page for clickable. | Back button size is unable to click .
Defect_15 | Ingame sound is merging with music after reverting back from gameplay. | 13-03-2024 | Critical | Medium | Closed | Closed | 0.1 | Functional | After exiting gameplay, the in-game sound should stop, and only the background music should continue playing without merging of sounds. | Ingame sound and music are merging after exit of game mode.
Defect_16 | Alignment is missing for player profile (level number in shield ) | 13-03-2024 | Minor | Low | Closed | Closed | 0.1 | Non-Functional | Level number should be shown with better alignment. | Level number alignment is missing. | the level up shown in the shield
Defect_17 | Race results page is displaying the incorrect position of the player . | 13-03-2024 | Major | Medium | Closed | Closed | 0.1 | Functional | Race results page should show players position according winner. | Player position is displaying incorrect though player is winner of the game.
Defect_18 | In level-4 cars are spawning at the finish point. | 14-03-2024 | Critical | High | Closed | Closed | 0.1 | Functional | Cars should move as usual till level complete without unusual spawn. | Cars are spawning at the finish point of the level in game.
Defect_19 | In level complete page duration of the level is displaying incorrect | 14-03-2024 | Minor | Low | Closed | Closed | 0.1 | Functional | Duration of the level should match exact time in game after finishing the level. | Duration of the level is not matching instead fixed time for every level.
Defect_20 | Against the clock-theme, In level-8 a single opponent car is moving backward. | 14-03-2024 | Critical | Medium | Closed | Closed | 0.1 | Functional | Cars should be move in forward direction for better gaming challenges. | Cars are moving
Defect_21 | In night themes car images are displaying darker while begining the race. | 14-03-2024 | Minor | Low | Closed | Closed | 0.1 | Non-Functional | Cars should be bright in night themes for visibility. | Cars are a bit darker due to less light on cars while racing
Defect_22 | Selected Level's are highlighting from 9th level. | 14-03-2024 | Critical | Low | Closed | Closed | 0.1 | Functional | Selected level should be highlighted with a mark on level image from begining. | Level's are not highlighting from the begining instead from 9th level
Defect_23 | 14th car is not moving forward after the animation in game. | 14-03-2024 | Major | Medium | Closed | Closed | 0.1 | Functional | After begining the game car should able to move to finish the race. | Car is not moving ahead in level after animation of cars race.
Defect_24 | In level against clock prix beach no collider besides the road. | 13-02-2024 | Major | Medium | Open |  | 0.1 | Non-Functional
Defect_25 | In certain level at particular point game is getting crashed. | 16-02-2024 | Critical | High | Open |  | 0.1 | Functional
Defect_26 | Game controls are not working in settings page. | 2024-09-03 | Major | Medium | Open | Done | 0.1 | Functional
Defect_27 | In settings page sensitivity is not working. | 2024-09-03 | Major | Medium | Open |  | 0.1 | Functional
Defect_28 | In Game car control for speed is too high. | 2024-09-03 | Major | Medium | Re-Open |  | 0.1 | Functional
Defect_29 | In game car tyres are not turning while we turn left/right. | 2024-09-03 | Minor | Low | Open |  | 0.1 | Functional |  |  | Done for 1 car
Defect_30 | Game screen is streched in some of the devices while install apk. | 2024-09-03 | Major | Medium | Open |  | 0.1 | Functional
Defect_31 | In Game while car crashing others objects/ cars animation is getting flickered. | 2024-09-03 | Major | Medium | Open |  | 0.1 | Non-Functional
Defect_32 | Level's are shuffling if we repeat the same game from level selection page in challenge mode. | 2024-09-03 | Critical | High | Open |  | 0.1 | Functional
Defect_33 | In challenge mode for level collider missing on the track.(Aeroplane Image for theme before begin) | 2024-09-03 | Critical | Medium | Open |  | 0.1 | Non-Functional
Defect_34 | In challenge mode after challenge completed level unlocked popup raising. | 2024-09-03 | Critical | Medium | Open |  | 0.1 | Non-Functional
Defect_35 | Boss race daily drifting(Level-4) theme colliders are missing at tunnel . | 2024-11-03 | Major | Medium | Open |  | 0.1 | Non-Functional
Defect_36 | In against the concrete jungle theme colliders are missing besides road.(after completing 10% level ) | 2024-11-03 | Major | Medium | Open |  | 0.1 | Non-Functional
Defect_37 | In snowy level at level complete both FINISH board and GO board are reflecting.(Showing wrong way) | 13-03-2024 | Major | Medium | Open | Done | 0.1
Defect_38 | Exhaust sound should be changed. | 13-03-2024 | Major | Medium | Open |  | 0.1 | Functional
Defect_39 | Time duration is turning into negative values.(for a given time-Against the clock theme) Level-3,8. | 13-03-2024 | Critical | Medium | Open |  | 0.1 | Functional
Defect_40 | Car is getting crashed even after level finished.(Car animation should be added for better game reality) | 13-03-2024 | Critical | High | Re-Open | Done | 0.1 | Functional |  |  | Animation we do later
Defect_41 | In pause page Ingame sound(car sound) is playing instead of music. | 13-03-2024 | Critical | Medium | Re-Open | Done | 0.1 | Functional
Defect_42 | Level comeplete is displaying victory even if out from out of time range in clock theme and out of checkpoints time way point to arctic theme. | 13-03-2024 | Critical | High | Progress(Need to check) |  | 0.1 | Functional
Defect_43 | Lightning should be added for the snow related themes for better quality car images.(6th level) | 13-03-2024 | Major | Medium | Re-Open | Done | 0.1 | Functional
Defect_44 | If we play unlocked level for 2-3 continously we are getting level unlocked popup for locked level. | 13-03-2024 | Critical | High | Open | Colose | 0.1 | Functional |  |  | its about player level up not for levels
Defect_45 | Even if we win the level, we are getting 2nd position in the results page.(Level-4) | 13-03-2024 | Critical | High | Re-Open | Done | 0.1 | Functional
Defect_46 | 2nd Position also victory for 2nd and (sometimes) 4th level . | 13-03-2024 | Major | Medium | Open |  | 0.1 | Functional |  |  | Level win is is specifed by diffrent modes ,1st two player wil win
Defect_47 | In night themes finish board is not displaying with light. | 14-03-2024 | Minor | Low | Open | Done | 0.1 | Non-Functional
Defect_48 | Unlocked next level popup is not getting after 8th level. | 14-03-2024 | Major | Medium | Open |  | 0.1 | Functional |  |  | that pop is not for levels its about player level up
Defect_49 | When we respan the car moving backward direction .prix beach-11(but not every time) | 14-03-2024 | Critical | High | Open | In editor is working fine check Ones | 0.1 | Functional |  |  | In editor is working fine check Ones
Defect_50 | In level 4 player position and speed trap count is not increasing in-game. | 15-03-2024 | Minor | Low | Open | Done | 0.1 | Functional
Defect_51 | In level-13 Elemination mount eve theme,even if time is out of range level turns to victory. | 15-03-2024 | Critical | Medium | Open | Done | 0.1 | Functional |  |  | player fave to be at 1 pos before time ends (time will repete till all players get elemenate ) 1 player willl b win or if we reach finish before elimanaction we will win
Defect_52 | Exhaust sound for cars in-game will be audible alternate in motion. | 15-03-2024 | Major | Medium | Re-Open |  | 0.1 | Functional | Sound should be getting for both nitro and pink bar while cross with car in in-game. | If race across the pink bar we'll get exhaust sound and then if we use nitro it won't get sound.
Defect_53 | Whenever we open career mode camera should be at last unlocked level. | 15-03-2024 | Major | Medium | Re-Open | Done | 0.1 | Non-Functional
Defect_54 | For all level's mini map is not displaying. | 15-03-2024 | Minor | Low | Open |  | 0.1 | Functional
Defect_55 | Level selection page is displaying top of the page.(100th level) | 15-03-2024 | Major | Medium | Open | Done | 0.1 | Non-Functional
Defect_56 | Even the level bar is not fully loaded it's displaying level unlocked popup. | 15-03-2024 | Major | Medium | Open |  | 0.1 | Functional
Defect_57 | If we use nitro, decreasing the speed but actual movement of car is speed. | 15-03-2024 | Major | Medium | Open | after the booster finish speed meter getting to its normal speed speed is reduced after booster finish | 0.1 | Functional
Defect_58 | At level finish board cross white lines are on air not on road. | 15-03-2024 | Major | Low | Open | I adjusted for certain levels if it is there repeating note the level No | 0.1 | Non-Functional
Defect_59 | Drifiting functionality is not updating drifitng points even we perform functionality. | 19-03-2024 | Minor | Medium | Open | Done | 0.1 | Functional
Defect_61
Defect_62
Defect_63
Defect_64
Defect_65
Defect_66
Defect_67
Defect_68
Defect_69
Defect_70